## Gantt Workplan
MTS GTM Workplan — Khoi Nguyen ¦ April–October 2026 ¦ Target: 10 buildings/month
ID | Workstream | Task | Owner | Start | End | Deliverable | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
[7 empty] | 14 Apr | 21 Apr | 28 Apr | 5 May | 12 May | 19 May | 26 May | 2 Jun | 9 Jun | 16 Jun | 23 Jun | 30 Jun | 7 Jul | 14 Jul | 21 Jul | 28 Jul | 4 Aug | 11 Aug | 18 Aug | 25 Aug | 1 Sep | 8 Sep | 15 Sep | 22 Sep | 29 Sep | 6 Oct
FOUNDATION
1.1 | FOUNDATION | Audit HubSpot lead database — export, segment by size/location/last touch | Khoi | W1 | W2 | Segmented lead list with reactivation plan | bar: W1 14 Apr to W2 21 Apr
1.2 | FOUNDATION | Learn pipeline tools (HubSpot, Zendesk, Google Ads account) | Khoi | W1 | W2 | Can operate independently | bar: W1 14 Apr to W2 21 Apr
1.3 | FOUNDATION | Absorb MTS value prop — 5 pain points, proposals, Zendesk proof metrics | Khoi | W1 | W2 | Can articulate MTS differentiation | bar: W1 14 Apr to W2 21 Apr
1.4 | FOUNDATION | Take over inbound lead intake from Bill | Khoi | W2 | W26 | Bill removed from lead intake permanently | bar: W2 21 Apr to W26 6 Oct
1.5 | FOUNDATION | Execute Google Ads quick wins — redirects, pause /trust_value, kill 2024 offer, fix typo | Khoi | W1 | W2 | ~$866/month waste eliminated | bar: W1 14 Apr to W2 21 Apr
1.6 | FOUNDATION | Document pricing rules (from Bill's head into a reference doc) | Bill/Khoi | W1 | W3 | Khoi can draft proposals independently | bar: W1 14 Apr to W3 28 Apr
LANDING PAGES & GOOGLE ADS
2.1 | LANDING PAGES & GOOGLE ADS | Rebuild /responsive-service/ page — new copy, real Zendesk metrics, capacity argument | Khoi | W3 | W5 | New page live | bar: W3 28 Apr to W5 12 May
2.2 | LANDING PAGES & GOOGLE ADS | Build new Changing Strata Manager page — replaces /change-strata/ | Khoi | W4 | W6 | New page live, keywords pointed | bar: W4 5 May to W6 19 May
2.3 | LANDING PAGES & GOOGLE ADS | Build Defects Playbook landing page — campaign-specific | Khoi | W5 | W7 | Campaign page live | bar: W5 12 May to W7 26 May
2.4 | LANDING PAGES & GOOGLE ADS | Build Insurance Review landing page — campaign-specific | Khoi | W7 | W9 | Campaign page live | bar: W7 26 May to W9 9 Jun
2.5 | LANDING PAGES & GOOGLE ADS | Build Sinking Fund / Capital Works landing page | Khoi | W9 | W11 | Campaign page live | bar: W9 9 Jun to W11 23 Jun
2.6 | LANDING PAGES & GOOGLE ADS | Implement tracking — UTMs, HubSpot↔Google Ads, gclid, lifecycle events | Khoi | W3 | W5 | End-to-end tracking operational | bar: W3 28 Apr to W5 12 May
2.7 | LANDING PAGES & GOOGLE ADS | Weekly search terms review + negative keyword maintenance | Khoi | W3 | W26 | Ongoing — weekly then fortnightly | bar: W3 28 Apr to W26 6 Oct
2.8 | LANDING PAGES & GOOGLE ADS | Monitor quality scores post-LP changes (2-4 week lag) | Khoi | W7 | W26 | QS improving on top 5 keyword groups | bar: W7 26 May to W26 6 Oct
2.9 | LANDING PAGES & GOOGLE ADS | Scale budget — $5.2k→$8k (W13), →$10k (W17), →$12k (W21) | Bill/Khoi | W13 | W26 | Budget scaled based on CAC data | bar: W13 7 Jul to W26 6 Oct
OLD LEAD DATABASE CAMPAIGN
3.1 | OLD LEAD DATABASE CAMPAIGN | Design re-engagement campaign — offer, messaging, case study selection, email sequence | Khoi | W2 | W3 | Campaign design complete | bar: W2 21 Apr to W3 28 Apr
3.2 | OLD LEAD DATABASE CAMPAIGN | Create proof pack — 3 case study one-pagers with real Zendesk metrics | Khoi | W3 | W5 | 3 case studies published | bar: W3 28 Apr to W5 12 May
3.3 | OLD LEAD DATABASE CAMPAIGN | Launch Segment 1 — most recent enquiries (last 6 months), highest intent | Khoi | W4 | W8 | Outreach complete, calls booked | bar: W4 5 May to W8 2 Jun
3.4 | OLD LEAD DATABASE CAMPAIGN | Launch Segment 2 — older enquiries (6-18 months), re-engage with new offer | Khoi | W6 | W12 | Outreach complete | bar: W6 19 May to W12 30 Jun
3.5 | OLD LEAD DATABASE CAMPAIGN | Launch Segment 3 — oldest viable contacts, final pass | Khoi | W10 | W16 | Database fully worked | bar: W10 16 Jun to W16 28 Jul
3.6 | OLD LEAD DATABASE CAMPAIGN | Follow-up sequences on all non-responders (text→email+case study→call→email 2) | Khoi | W4 | W18 | Multi-touch nurture running | bar: W4 5 May to W18 11 Aug
SBBIS & DEFECTS TARGETING
4.1 | SBBIS & DEFECTS TARGETING | Set up NSW Strata Search scraping agent — identify recently registered strata plans | Khoi/Quang | W3 | W5 | Agent producing weekly list | bar: W3 28 Apr to W5 12 May
4.2 | SBBIS & DEFECTS TARGETING | Build target list — filter for buildings approaching 12-month renewal window | Khoi | W4 | W6 | Prioritised target list | bar: W4 5 May to W6 19 May
4.3 | SBBIS & DEFECTS TARGETING | Develop Defects Playbook campaign collateral — SBBIS claims process guide | Khoi | W5 | W7 | Playbook content ready | bar: W5 12 May to W7 26 May
4.4 | SBBIS & DEFECTS TARGETING | Launch outbound to new registrations — Defects Playbook as lead magnet | Khoi | W7 | W26 | Ongoing weekly outbound | bar: W7 26 May to W26 6 Oct
4.5 | SBBIS & DEFECTS TARGETING | Launch outbound to 12-month renewal buildings — renewal timing pitch | Khoi | W8 | W26 | Ongoing outbound to renewal buildings | bar: W8 2 Jun to W26 6 Oct
4.6 | SBBIS & DEFECTS TARGETING | Build Google Ads campaign targeting defects/SBBIS keywords | Khoi | W8 | W10 | Paid campaign live | bar: W8 2 Jun to W10 16 Jun
LARGE BUILDING KEY ACCOUNT
5.1 | LARGE BUILDING KEY ACCOUNT | Define target criteria — lot count (50+), Sydney geography, high-value buildings | Khoi/Bill | W5 | W7 | Target criteria documented | bar: W5 12 May to W7 26 May
5.2 | LARGE BUILDING KEY ACCOUNT | Research and build target list — 20-30 large buildings with contacts/pain signals | Khoi | W7 | W10 | Researched target list | bar: W7 26 May to W10 16 Jun
5.3 | LARGE BUILDING KEY ACCOUNT | Develop key account approach — personalised outreach, tailored proposals | Khoi/Bill | W9 | W11 | Key account playbook | bar: W9 9 Jun to W11 23 Jun
5.4 | LARGE BUILDING KEY ACCOUNT | Launch key account outreach — 1-2 targets per week | Khoi/Bill | W11 | W26 | Ongoing — Bill takes discovery calls | bar: W11 23 Jun to W26 6 Oct
5.5 | LARGE BUILDING KEY ACCOUNT | AGM targeting — identify large buildings with AGMs next quarter, time outreach | Khoi | W12 | W26 | AGM calendar tracked | bar: W12 30 Jun to W26 6 Oct
PIPELINE REPORTING & GOVERNANCE
6.1 | PIPELINE REPORTING & GOVERNANCE | Build pipeline dashboard — leads by channel, conversions, CAC | Khoi | W3 | W5 | Dashboard operational | bar: W3 28 Apr to W5 12 May
6.2 | PIPELINE REPORTING & GOVERNANCE | Weekly pipeline review with Bill (15 min Friday) | Khoi/Bill | W4 | W26 | Standing meeting | bar: W4 5 May to W26 6 Oct
6.3 | PIPELINE REPORTING & GOVERNANCE | Monthly funnel analysis — conversion rates by stage/channel/campaign | Khoi | W8 | W26 | Monthly report to Bill | bar: W8 2 Jun to W26 6 Oct
AI GTM PLATFORM ARCHITECTURE
7.1 | AI GTM Platform | Document manual workflows as-built — every step Khoi executes, inputs/outputs, systems used, time per step | Khoi | W4 | W8 | Workflow documentation complete | bar: W4 5 May to W8 2 Jun
7.2 | AI GTM Platform | Map data flows between systems — HubSpot ↔ Zendesk ↔ Google Ads ↔ StrataMax ↔ website | Khoi/Quang | W6 | W9 | Integration map delivered | bar: W6 19 May to W9 9 Jun
7.3 | AI GTM Platform | Identify automation candidates — rank each workflow step by: automatable (Y/N), ROI, complexity, human judgement required | Khoi | W8 | W10 | Prioritised automation backlog | bar: W8 2 Jun to W10 16 Jun
7.4 | AI GTM Platform | Define AI agent specifications — what each agent does, inputs, outputs, guardrails, human-in-the-loop points | Khoi/Quang | W9 | W11 | Agent specs mapped to AI CMO swarm | bar: W9 9 Jun to W11 23 Jun
7.5 | AI GTM Platform | Deliver AI GTM Architecture Spec — full document for engineering handover | Khoi | W11 | W12 | Spec delivered to Quang for build | bar: W11 23 Jun to W12 30 Jun
7.6 | AI GTM Platform | Begin automation build — HubSpot→Zendesk integration, lead scoring rules, nurture workflows | Khoi/Quang | W13 | W26 | First automations live | bar: W13 7 Jul to W26 6 Oct
7.7 | AI GTM Platform | Proposal automation — Claude Code /new-lead skill or Azure Function for template filling | Khoi/Quang | W14 | W20 | Proposals auto-generated from lead data | bar: W14 14 Jul to W20 25 Aug
7.8 | AI GTM Platform | Outbound automation — scraper → target list → outreach trigger pipeline | Khoi/Quang | W16 | W22 | Automated prospecting pipeline | bar: W16 28 Jul to W22 8 Sep

## Outcome Measures
MTS GTM Outcome Measures — Target: 10 Buildings/Month
SECTION 1: Monthly Building Targets by Channel
Month | Google Ads | Old Lead DB | Defects/SBBIS | Large Building | Total Target | Actual | Variance | On Track?
Apr 2026 | 2.75 | 0 | 0 | 0
May 2026 | 4 | 1 | 0 | 0
Jun 2026 | 7 | 2 | 0.5 | 0
Jul 2026 | 10 | 2.5 | 1 | 0.5
Aug 2026 | 15 | 2 | 1.5 | 0.5
Sep 2026 | 18 | 1.5 | 1.5 | 1
Oct 2026 | 20 | 1.5 | 2 | 1
TOTAL (6 months)
SECTION 2: Google Ads Funnel KPIs — Optimise Then Scale
|  | ← PHASE A: OPTIMISE (same budget) → |  |  | ← PHASE B: SCALE BUDGET →
Metric | Current | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 6 Target
Ad Spend/month | $5,162 | $5,162 | $5,162 | $5,162 | $8,000 | $10,000 | $12,000 | $12,000
CPC | $8.40 | $8.00 | $7.20 | $6.30 | $6.30 | $6.30 | $6.30 | <$6.50
Clicks/month | 615 | 645 | 717 | 820 | 1,270 | 1,590 | 1,900 | 1,900
Click-to-form | 5.0% | 5.5% | 6.0% | 7.0% | 7.0% | 7.0% | 7.0% | >7%
Forms/month | 31 | 35 | 43 | 57 | 89 | 111 | 133 | 130+
Form-to-call | 50% | 52% | 55% | 62% | 62% | 62% | 62% | >60%
Calls/month | 15 | 18 | 24 | 35 | 55 | 69 | 82 | 80+
Call-to-won | 27.5% | 27.5% | 27.5% | 28% | 28% | 28% | 28% | >25%
Buildings won/month | 2.75 | 4 | 7 | 10 | 15 | 19 | 23 | 20+
CAC/building | $1,900 | $1,290 | $737 | $520 | $530 | $525 | $520 | <$600
Impression share | <10% | <10% | <10% | <10% | ~15% | ~19% | ~23% | >20%
SECTION 3: Campaign Outcome Measures
OLD LEAD DATABASE CAMPAIGN
Total viable contacts in DB | TBD (audit W1-W2)
Contacts reached | 100%
Response rate | >15%
Calls booked from responses | >30% of responses
Buildings won (total — finite pool) | 8–12
Campaign duration | W4–W18
Revenue impact | ~$80–96k new ARR
CAC per building | $0 ad spend (Khoi time only)
SBBIS & DEFECTS — NEW REGISTRATION TARGETING
New registrations scraped/month | TBD (agent output)
Buildings approaching 12-month renewal | TBD
Outreach contacts/month | 20+
Response rate | >10%
Discovery calls/month | 2–4
Buildings won/month | 1–2
Avg lots per building won | 15–30 (newer SBBIS buildings)
Revenue per building won/year | $9–18k ARR
Google Ads defects campaign cost/conv | Track separately from main campaigns
LARGE BUILDING KEY ACCOUNT STRATEGY
Target buildings researched | 20–30
Approaches made/month | 4–8
Committee meetings secured/month | 1–2
Proposals delivered/month | 1
Buildings won/quarter | 1 (70+ lots each)
Revenue per building won/year | $28k+ ARR (70 lots × $400/lot)
Payback period | N/A (no ad spend — Khoi + Bill time only)
Win rate on proposals | >40% (highly targeted)
SECTION 4: Milestone Gates — Scale Decisions
Gate | Condition | Target Date | Budget Decision | Status | Notes
Gate 1 | Google Ads producing 10+ bldgs/month at current $5.2k spend | Week 12 (Jul) | Scale budget to $8k/month
Gate 2 | CAC holds at <$600 at $8k spend | Week 16 (Aug) | Scale to $10k/month
Gate 3 | CAC holds at <$600 at $10k spend | Week 20 (Sep) | Scale to $12k/month
Gate 4 | Channel mix review — which campaigns delivering best ROI? | Week 13 (Jul) | Double down or pivot
Gate 5 | Lead database exhausted — shift Khoi time to outbound | Week 18 (Aug) | Reallocate hours
SECTION 5: AI GTM Platform — Architecture Deliverables
AI GTM PLATFORM (Business Asset)
Manual workflow documentation | Complete by W8 — every marketing + sales step documented
System integration map | Complete by W9 — HubSpot/Zendesk/Ads/StrataMax data flows
Automation priority backlog | Complete by W10 — ranked by ROI/complexity
AI agent specifications | Complete by W11 — maps to AI CMO swarm architecture
AI GTM Architecture Spec | Delivered W12 — engineering handover document
First automations live | W13+ — HubSpot→Zendesk, lead scoring, nurture workflows
Proposal automation | W14-W20 — auto-generated from lead data
Outbound automation | W16-W22 — scraper→target list→outreach pipeline
Platform covers marketing | Paid acquisition, landing pages, content, lead capture, scoring, nurture, campaign analytics
Platform covers sales | Proposal generation, pricing engine, pipeline management, follow-up, close support
AI GTM is a capital asset — it scales without headcount, transfers to a GM, and is a component of MTS's $20m Year 5 equity value. Khoi architects; Quang's team builds; the platform endures.

## 10 Buildings Roadmap
The Path to 10 Buildings/Month — Google Ads Optimisation Roadmap
CURRENT STATE |  |  |  |  | TARGET STATE (Month 3)
Buildings won/month | 2.75 |  |  |  | Buildings won/month | 10+
True CAC/building | $1,900 |  |  |  | True CAC/building | ~$520
Impression share | <10% |  |  | → | Impression share | <10% (same budget)
Forms/month | 31 |  |  |  | Forms/month | 57
Form-to-call rate | 50% |  |  |  | Form-to-call rate | 62%
Call-to-won rate | 27.5% |  |  |  | Call-to-won rate | 28%
Monthly ad spend | $5,162 |  |  |  | Monthly ad spend | $5,162 (unchanged)
WHAT GETS US TO 10 — Lever-by-Lever Bridge
# | Lever | Current | Target | Extra Bldgs/Month | When | Owner | How We Know It's Working
1 | Waste elimination + ad redirects | $866/mo wasted | $0 wasted | +1.0 | W1–W2 | Khoi | Spend redeployed to converting keywords
2 | CPC reduction (quality score fix) | $8.40 CPC | $6.30 CPC | +2.0 | W7–W12 | Khoi | Quality scores improving on top 5 keywords
3 | Landing page conversion lift | 5.0% click→form | 7.0% click→form | +2.5 | W5–W10 | Khoi | /responsive-service/ + new pages outperform old
4 | Form-to-call improvement | 50% | 62% | +1.5 | W3–W8 | Khoi | Fewer junk leads; Khoi follow-up converting non-responders
5 | Old lead database reactivation | 0 bldgs/month | 2–3 bldgs/month | +2.5 | W4–W12 | Khoi | Calls booked from dormant contacts
6 | Defects/SBBIS campaign | 0 bldgs/month | 0.5–1 bldgs/month | +0.75 | W7–W16 | Khoi | New registrations contacted, responses received
TOTAL INCREMENTAL |  |  |  | +10.25 | From 2.75 → ~13 buildings/month (exceeds 10 target)
EXPECTED MONTHLY PROGRESSION (Google Ads only, same budget)
Metric | Month 1 (May) | Month 2 (Jun) | Month 3 (Jul)
CPC | $8.00 | $7.20 | $6.30
Clicks | 645 | 717 | 820
Forms | 35 | 43 | 57
Calls | 18 | 24 | 35
Buildings won | 4 | 7 | 10
CAC/building | $1,290 | $737 | $520
KEY: All improvements from the SAME $5,162/month spend. No budget increase needed to hit 10 buildings. Scale budget AFTER proving the optimised funnel works.
AI GTM PLATFORM — 90-Day Architecture Deliverable
Khoi doesn't just execute the growth plan — he architects the AI system that replaces the manual work. Every workflow he runs manually becomes the spec for the automated platform. By Week 12, the AI GTM Architecture Spec is delivered to engineering.
Phase | Weeks | What Khoi Does | What It Becomes
Execute & Document | W4-W8 | Runs every GTM workflow manually, documents each step: inputs, outputs, systems, time, decisions | Requirements document for automation
Map & Prioritise | W8-W10 | Maps data flows between systems, identifies what's automatable, ranks by ROI vs complexity | Integration architecture + automation backlog
Specify | W9-W12 | Defines AI agent specs: what each does, guardrails, human-in-the-loop points. Maps to AI CMO swarm | AI GTM Architecture Spec — engineering handover
Build | W13-W26 | Works with Quang to build: HubSpot→Zendesk integration, nurture workflows, proposal automation, outbound pipeline | Live AI GTM platform — a business asset
ASSET VALUE: The AI GTM platform scales without headcount, transfers to a GM, feeds the Block/acquisition thesis, and is a component of MTS's $20m equity value at Year 5.